## Sheet1
Task | Start Date | Finish Date | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Planning | 1st Sept 2023 | 15th Sept 2023 | bar: Sept
SRS/SDS Document | 16th Sept 2023 | 1st Oct 2023 | bar: Sept to Oct
User Profile | 2nd Oct 2023 | 30th Oct 2023 | bar: Oct
Vendor Listing | 1st Nov 2023 | 30th Nov 2023 | bar: Nov
Customer Booking | 1st Dec 2023 | 5th Jan 2024 | bar: Dec to Jan
Final FYP1 | 5th Jan 2024 | 30th Jan 2024 | bar: Jan
Filter and Search | 1st Feb 2024 | 28th Feb 2024 | bar: Feb
Review and Rating | 1st Mar 2024 | 20th Mar 2024 | bar: Mar
Scheduling | 21st Mar 2024 | 10th Apr 2024 | bar: Mar to Apr
Admin Portal | 11th Apr 2024 | 11th May 2024 | bar: Apr to May
Testing | 12th May 2024 | 20th May 2024 | bar: May
Final FYP2 | 21st May 2024 | 5th Jun 2024 | bar: May to Jun